**Refreshing *The New Zealand Curriculum***

**Indicative Timeline (2021-2025)**

This narrative identifies indicative timelines for the different work programmes within the refresh. Where appropriate, timelines entries are shown as part of these work streams: The New Zealand Curriculum (NZC); Curriculum Supports (CS); Engagement, Communication and Capability Building (ECCB).

Three values are a focus throughout this indicative timeline: trust, coherence and equity.

**2018**

1. Kōrero Mātauranga.

**2018 to midway through 2019**

1. Engagement includes Curriculum, Progress and Achievement Ministerial Advisory Group and Reference Group.

**2019**

**June 2019**

1. Advice from the Curriculum, Progress and Achievement Ministerial Advisory Group.

**September 2019**

1. Prime Minister announces Aotearoa New Zealand’s histories will be taught in schools and kura in 2022; Minister announces intention to refresh the national curriculum.

**September 2019 to December 2020**

1. Curriculum working groups advise on scope and process for refreshing the national curriculum; Draft curriculum content design for Aotearoa New Zealand’s histories designed and tested.
2. **2020**

**August 2020 (term 3 onwards)**

1. (CS) New Professional Learning and Development priorities ready for use.
2. **2021**

**2021 to 2024**

1. (CS) Records of Learning progressively designed and tested.

**2021 to 2025 and beyond**

1. (ECCB) Engagement, communication and capability building.

**2021 to 2025**

1. (CS) NZC implementation support designed, tested and ready for use.

**February 2021**

1. Minister announces next steps for national curriculum refresh.

**February-May 2021**

1. (NZC) Draft Aotearoa New Zealand’s histories (ANZH) content out for public consultation.

**March 2021**

1. (CS) Literacy and Mathematics strategies underway.

**April 2021**

1. (NZC) Social Sciences Writing Group established; Curriculum Voices Group – NZC established; Bicultural and Inclusive Framework Working Group established.

**May-September 2021**

1. (NZC) NZC framework and vision co-designed and tested; Social Sciences content designed and tested.

**May 2021**

1. (CS) Curriculum leads introduced

**October 2021**

1. (CS) New Online Curriculum Hub – design work underway progressively.

**2022**

**2022 to 2023**

1. (NZC) Social Sciences content ready for use.
2. (CS)Mathematics and Statistics, English and Science content designed and tested

**2022 to 2025**

1. (NZC) NZC framework trialled progressively.
2. (CS) Te Kete Ipurangi (TKI) progressively replaced with new Online Curriculum Hub.

**2023**

**2023 to 2024**

1. (NZC) Mathematics and Statistics, English and Science content ready for use; Technology, the Arts, Learning Languages, Health and Physical Education content designed and tested.

**2024**

**2024 to 2025**

1. (NZC) Technology, the Arts, Learning Languages, Health and Physical Education content ready for use.

**2025**

1. (NZC) All schools using refreshed curriculum by the end of 2025, and Records of Learning ready for use; Implementation and support for refreshed NZC continues.

**Note:** (NZC) As areas are refreshed and curriculum supports are introduced, they enter a cycle of continuous improvement.

ENDS