**NCEA Change Programme**

**Indicative timeline (2021-2025)**

The following narrative identifies indicative timelines for the different work programmes within the NCEA Change Programme. Where appropriate, timelines entries are shown as part of these work streams: Design (DES); Public Engagements (PUB); Pilots (PIL); Implementation (IMP) and Accord Teacher Only Days (ACC).

Three values are a focus throughout this indicative timeline: trust, coherence and equity.

**2018**

Minister of Education launches NCEA Review, part of Kōrero Mātauranga.

**2019**

Government announces NCEA Change Package.

**2020**

**February 2020**

Government confirms NCEA Change Programme.

**2021**

**Until July 2021**

(DES) Develop NCEA Level 1 standards for NZC subjects and TMoA Wāhanga ako (learning areas).

**January 2021 to December 2022**

(DES) Te Reo Matatini me te Pāngarau | Literacy and Numeracy standards, assessments, and guidance.

**January-December 2021**

(PIL) Te Ao Haka (across all three NCEA levels) *[36 schools and kura].* NCEA Level 1 English, Science, Religious Studies, and Visual Arts *[25 schools].*

**January-March 2021**

(PUB) Draft NCEA Level 1 TMoA Phase 1 subject content; This phase consists of Learning Matrices, teaching, learning and assessment guidance, sample Course Outlines, and Assessment Matrices (indicative standard titles only). Draft Te Reo Matatini me te Pāngarau standards.

**January 2021 to June 2023**

(DES) Vocational Entrance Award - design, trialling, and revision.

**From February 2021**

(IMP) New rules for Course Endorsements and Resubmissions.

**March-April 2021**

(PUB) Draft NCEA Level 1 NZC Phase 1 subject content.

**May 2021**

(ACC) Teacher Only Day Mana ōrite mō te mātauranga Māori; Te Reo Matatini me te Pāngarau | Literacy and Numeracy.

**June-August 2021**

(PUB) Provisional subject lists for NCEA (Public engagement for provisional subject lists for NZC NCEA Levels 2 and 3 and TMoA NCEA Levels 1-3.

**July 2021**

(IMP) Te Reo Matatini me te Pangarau | Literacy and Numeracy –

Detailed guidance around transitional arrangements for learners.

(DES)Te Reo Matatini me te Pangarau | Literacy and Numeracy –

Regional support package trialled.

 **July-August 2021**

(PUB) Expression of Interest: TMoA Level 1 pilot.

**July-December 2021**

(PIL) Te Reo Matatini me te Pāngarau | Literacy and Numeracy *[13 schools, 6 kura and 2 tertiary providers].*

**August 2021**

(PUB) Expressions of Interest: Te Reo Matatini me te Pāngarau | Literacy and Numeracy pilot, NZC NCEA Level 1 pilot and Te Ao Haka pilot. TMoA Phase 1 and Phase 2 subject content (This phase includes Achievement Standards, Internal Assessment Activities, Conditions of Assessment, and revised Phase 1 materials).

Draft NZC NCEA Level 1 subject content released for feedback.

(ACC) Teacher Only Day NCEA Level 1 Review of Achievement Standards.

**September 2021**

(IMP) Final subject lists for NCEA Levels 2 and 3 announced.

**September 2021 to September 2022**

(DES) Develop NCEA Level 2 standards for NZC subjects and TMoA Wāhanga ako.

**October-November 2021**

(PUB) Draft Phase 1 materials for some NZC NCEA Level 2 subjects released *[Learning Matrices, Assessment Matrices, sample Course Outlines, and teaching, learning and assessment guidance].*

**November-December 2021**

(ACC) Teacher Only Day Local Curriculum Design.

**2022**

**During 2022**

(PUB) Draft NCEA Level 2 NZC and TMoA subject content (same process as Level 1).

(ACC) Four Accord Teacher Only Days.

**February 2022**

(PUB) Draft Phase 1 materials for the rest of NZC NCEA Level 2 subjects released.

**February-December 2022: Wider pilots**

(PIL) Te Reo Matatini me te Pāngarau | Literacy and Numeracy (wider pilot). Te Ao Haka (150+ schools and kura). All NZC NCEA Level 1 subjects (250+ schools and kura). All TMoA NCEA Level 1 Wāhanga Ako (Phase 1 and 2 subject content are revised again following piloting).

**August 2022**

(PUB) Draft Phase 2 materials for all new NCEA Level 2 subjects (for both NZC and TMoA) released *[Achievement Standards, Assessment Activities, teaching, learning and assessment guidance, Conditions of Assessment, redeveloped Course Outlines, etc].*

**September 2022 to September 2023**

(DES) Develop NCEA Level 3 standards for NZC subjects and TMoA Wāhanga Ako.

**2023**

**During 2023**

(PUB) Draft NCEA Level 3 NZC and TMoA subject content (same process as NCEA Level 1).

**February-December 2023**

(PIL) All NZC NCEA Level 2 subjects. All TMoA NCEA Level 2 Wāhanga Ako. Vocational Excellence Award.

**From February 2023**

(IMP) NCEA Level 1 subjects and Wāhanga Ako. Te Ao Haka (across all three NCEA levels). Te Reo Matatini me te Pāngarau | Literacy and Numeracy (mandatory co-requisite).

**From September 2023**

(NCEA IMP) Vocational Entrance Award.

**2024**

Pilots.

**February-December 2024**

(PIL) All NZC NCEA Level 3 subjects. All TMoA NCEA Level 3 Wāhanga Ako.

**From February 2024**

(IMP) NCEA Level 2 subjects and Wāhanga Ako.

**2025**

**From February 2025**

(IMP) NCEA Level 3 subjects and Wāhanga Ako.

ENDS