**Supporting the implementation of *Te Whāriki***

**Indicative timeline (2021-2025)**

This workprogramme supports the implementation of *Te Whāriki* in line with *He taonga te Tamaiti – Every child a taonga, early learning action plan 2019-2029.*

This narrative identifies indicative timelines for the different work programmes. Where appropriate, timeline entries are shown as part of these work streams: Gazette the curriculum framework, *Te Whāriki*, to support engagement with the principles, strands, goals and learning outcomes when designing local curricula (GAZ); Develop a sustained and planned approach to professional learning and development (DEV); Support the workforce to integrate te reo Māori into all early learning services (SUP); Construct a range of valid, reliable, culturally appropriate tools to support formative assessment and teaching practice (CON); and tools and resources to support the implementation of *Te Whāriki* (TOOL).

Three values are a focus throughout this indicative timeline: trust, coherence and equity.

**2018**

* Consult on *He taonga te Tamaiti: Strategic Plan for Early Learning 2019-2029.*

**2019**

* Publish *He taonga te Tamaiti: Early Learning Action Plan 2019-2029.*

**2020**

**October 2020 to June 2021**

(CON) Four Sector Reference Group (SRG) meetings.

**2021**

**2021-24**

(SUP) Te Ahu o te Reo Māori: Planning national delivery in all 10 ministry regions.

**January–July 2021**

(DEV) Review of EL PLD (Early Learning Professional Learning and Development).

**February 2021**

(CON) Final Frameworks for Practice and Progress Tools (P&PT) and Draft Social and Emotional Learning (SEL).

**March-May 2021**

(GAZ) Early engagement (Māori medium/Pacific Early Learning Services (ELS)/other interested stakeholders.

**May-June 2021**

(CON) Initial user testing on the SEL P&PT tool.

**May 2021**

(TOOL) Launch of refreshed *Te Whāriki* Online website.

**June 2021 to June 2022**

(CON) Develop an oral language and literacy P&PT (supported by Te Kōrerorero).

**August 2021 to June 2022**

(CON) Wider PLD supported trial of SEL P&PT.

**August-September 2021**

(DEV) Advice to Minister on EL PLD.

**September 2021**

(GAZ) Cabinet approval to consult on gazette notice

**Sept-Oct 2021**

(GAZ) Public consultation on expanding the gazetted framework for *Te Whāriki.*

**September 2021**

(SUP) Launch resources for Māori medium early learning services.

**End of 2021**

(GAZ) Gazette Notice published.

**2022**

Please note, the following projections are tentative and subject to approvals including budgetary decisions.

**January-December 2022**

(TOOL) A range of resources to support local curriculum design aligned with *Te Whāriki* (2017) developed and launched on the website.

(GAZ) Jan - June 2022 – resources and guidance to support Gazette implementation.

**Mid 2022**

(DEV) SELO PLD panel renewed; Co-design a sustained PLD programme (including procurement).

**June 2022**

(SUP) Te reo Māori language acquisition resources for Māori medium early learning services

**September 2022 to September 2023**

(CON) Develop a mathematics P&PT and mathematics resource.

**2023**

**From early 2023**

(DEV) Begin roll out sustained programme of *Te Whāriki* Implementation, including: SEL and oral language P&PT.

**February-May 2023**

(TOOL) Procure provider to maintain and develop *Te Whāriki* Online (current contract expires June 2023).

**Mid 2023**

(DEV) Co-design leadership PLD.

**September 2023**

(CON) Release of mathematics resource and P&PT and PLD.

**Late 2023**

(DEV) Go to market for sustained programme of leadership PLD.

**2024**

**Early 2024**

(DEV) Begin roll out of leadership PLD.

**2025**

(CON) Review of PLD/P&PT and identify next steps.

ENDS